M4 Water Drop Suppression: Quantified Uncertainty, Version 1.1

NASA Aerial Wildfire Project, ACERO Disaster Lab working group. 20 October 2026. Version 1.1. Standard day for every mission and fire: 24 h, 06:00 to 06:00 local, on the peak-run day. GOFER not used.

Bottom line

No drone in the project library has dropped water. Every M4 aircraft is a test or demonstrator (W5), so v1.1 quantifies what the weather allowed, not what was done.

32 to 53 m of drift. A release from 30 m (assumed) in Camp's standard-day wind (29 mph sustained, 48 mph gusts) moves the load that far before any aiming correction.

LNU's overnight run was flyable for a 30 kt aircraft. From 20:00 to 06:00 on 18 to 19 August, Atlas Peak gusts allowed a 30 kt (34.5 mph) aircraft in 100% of hours and an Alta X in 70%, while the first complex ICS-209 did not exist until 08:00 on 19 August.

Who uses it

Incident commander, operations section chief and air tactical group supervisor: they order and sequence drops and need the chance a drop lands on target, especially when crewed aircraft stand down at night. Crews on the line: they work under the drop, so drift and timing are also a safety number.

Aircraft for M4 (W5 unless noted)

| Aircraft | Status | Load | Wind / night | M4 role |
| --- | --- | --- | --- | --- |
| Rain and Sikorsky autonomous Black Hawk / Firehawk | Demonstrator; CAL FIRE agreement 2025 | 324 gal bucket (demo); 1,000 gal tank class | Gusts to 30 kt; aimed at night and smoke | Night direct attack at helicopter scale |
| Seneca Argo-1 swarm (5 drones) | Tested by CAL FIRE, July 2026 | 20 gal water plus foam each | Not found; IR targeting | Initial attack on small fires |
| FireSwarm Thunder Wasp GT | Tested (XPRIZE finalist) | Up to 100 gal | Not found | Initial attack; bulk water |
| Large UAS or optionally piloted aircraft | Concept (ConOps 2026, p.19) | Bulk water | Night by design | Night water drop instead of retardant |

How the uncertainty is quantified

Water on target per hour: V_eff = n x S x V x P(hit) x p, n aircraft, S = 60 / (2 transit + drop + turnaround) sorties per hour, V load, p wind gate. Drift d = u x sqrt(2h/g) = u x 2.47 s at h = 30 m; P(hit) = Φ((w - d_res)/σ) - Φ((-w - d_res)/σ) for target half-width w, aim error σ and residual drift d_res. Wind enters through p and d.

| Critical window | Sust. / gust mph | Drift m (30 m) | Gust spread m | p, 30 kt | p Alta X, nights |
| --- | --- | --- | --- | --- | --- |
| Camp | 29 / 48 | 32 to 53 | 21 | 58% | 62% |
| LNU | 29 / 41 | 32 to 45 | 13 | 83% | 92% |
| Carr | 9 / 21 | 10 to 23 | 13 | 100% | 100% |
| Pioneer | 9 / 25 | 10 to 28 | 18 | 100% | 99% |

Kinds of uncertainty: the gust spread is drift an aim on sustained wind cannot remove; this is a no-drag, instant-wind estimate from 20 ft winds, and drag and stronger flight-level wind push it in opposite directions. Throughput: Week 6 records about 35 L/h for a small drone against 10,345 L/h for a large airtanker. v1.2 needs: measured drop accuracy against wind from the Seneca and Firehawk tests; release heights and loads per aircraft.

Night

In the ConOps future state a night water drop would only require a large UAS or optionally piloted aircraft, and the same water could be shared across many small to medium UAS hitting the flame front in a daisy chain (ConOps 2026, p.19). No aircraft in project records has done it. LNU has no aircraft perimeter series in the record, so night growth is not computed without GOFER. On Camp, 4% of the 28 aircraft perimeters were stamped between 20:00 and 06:00, while about 46% of the growth between perimeters fell in those hours (growth spread evenly between perimeters).

Hour by hour, standard day: LNU, 18 August 06:00 to 19 August 06:00 PDT (Atlas Peak RAWS)

| Hour (N = night) | Aircraft perimeter (age) | ICS-209 (age) | Wind mph sust/gust, RH | Alta X / T1 30 | What the records show | Drone task from this hour |
| --- | --- | --- | --- | --- | --- | --- |
| 18 Aug 06 | none | none | 0/7, 41% | fly/fly |  | Morning: drones map which drops held and where to drop next |
| 07 | none | none | 4/9, 45% | fly/fly |  |  |
| 08 | none | none | 3/8, 39% | fly/fly |  |  |
| 09 | none | none | 1/6, 36% | fly/fly |  |  |
| 10 | none | none | 5/7, 37% | fly/fly |  |  |
| 11 | none | none | 8/10, 30% | fly/fly |  |  |
| 12 | none | none | 10/15, 25% | fly/fly | Satellite (VIIRS) 7,328 ac for the main object |  |
| 13 | none | none | 15/21, 27% | fly/fly |  |  |
| 14 | none | none | 23/28, 28% | no/fly |  | Daylight: helicopter and airtanker drops; drones map where drops held |
| 15 | none | none | 22/29, 25% | no/fly |  |  |
| 16 | none | none | 26/36, 24% | no/no |  |  |
| 17 | none | none | 28/36, 23% | no/no |  |  |
| 18 | none | none | 29/41, 17% | no/no | Atlas Peak 29 mph sustained, 41 mph gusts |  |
| 19 | none | none | 26/39, 15% | no/no |  |  |
| 20 N | none | none | 17/29, 15% | no/fly | Overnight 18 to 19 Aug: fires merge in a 12-mile run (agency chronology) | Night: crewed aircraft stand down; night water drop is a large UAS or OPA concept only |
| 21 N | none | none | 15/24, 8% | no/fly |  |  |
| 22 N | none | none | 14/23, 13% | no/fly |  |  |
| 23 N | none | none | 13/22, 15% | fly/fly |  |  |
| 19 Aug 00 N | none | none | 11/18, 15% | fly/fly | Satellite (VIIRS) 41,602 ac for the main object | Night: drone IR shows where line held, ready for first light drops |
| 01 N | none | none | 10/15, 13% | fly/fly |  |  |
| 02 N | none | none | 5/11, 13% | fly/fly |  |  |
| 03 N | none | none | 7/12, 11% | fly/fly |  |  |
| 04 N | none | none | 7/10, 11% | fly/fly |  |  |
| 05 N | none | none | 9/15, 10% | fly/fly |  |  |

Sources, all in the project folder: Weather Data (RAWS 10-min mean at 20 ft, gust = prior-hour peak); perimeter_supplements time-area records, GOFER rows dropped; Week 6 workbook; UQ proposal v0.5 (W5 = Week 5). Drone tasks and values marked assumed are our proposals, not records.